Advising Improvement Team
Roadmap

| Advising is streamlined and outcome driven; creating student ownership, shared vision, and a clearly defined process |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action Item | Assessment | Assessment Outcome | Individual Responsible | Time line |
| Selecting advisors | % of students who chose an advisor | 100% of students | Joan, Zeda, and Mike | Before November 1, 2009 |
| Developing Advisor & Advisee Handbook | -Satisfaction survey -Completion on Handbook | Completed | Joanna, Gin, and Deltha | By August 1 |
| Advisor Training | -Survey of participants at training -Survey of students/Graduate survey | Increased satisfaction | Karen, Joanna, James, Holly. And Mike | Fall In-service then throughout the semester |
| Forms available online | -Forms are online | 100% | Ron and Mike | Immediately |
| Be Advised Campaign | -# of students advised | 10% increase over previous semester | Mike, Ron, Joan, James, Kim Whitten, Zeda, and Russell Bassham | April 1 - May 8, 2009 |
| Student Success Class | -Student evaluations -Faculty evaluations | 80% student satisfaction 90% Faculty satisfaction | Deltha, Holly, Joan, Jenny, Ron, and Mike | Summer 2009 |